## Sheet1
id | hull_no | ship_type | size | buyer_comment | builder_reply | extra | credit | remark
11869 | 8000 | LNGC | 174K | We request the installation of a hybrid SOx scrubber system <s>instead of the open-loop type.</s> | Installation of a hybrid scrubber is technically possible. Compared to the open-loop system, it will require additional space and power consumption. A feasibility analysis will be submitted for your review. | 2500 |  | D:/Streamlit_UI/frontend/static/images/FWG.pdf
11539 | 8000 | LNGC | 174K | We request the Emergency Shut Down (ESD) system to be configured with full redundancy. | Redundant ESD system configuration is achievable within IMO requirements. This includes dual PLCs and <s>duplicated cabling for critical components. While this enhances operational safety,</s> additional space and cost implications are expected. |  |  | D:/Streamlit_UI/frontend/static/images/test_image.jpg
17041 | 8000 | LNGC | 174K | We prefer an electrolysis-type Ballast Water Treatment System (BWTS) instead of UV-type. | Electrolysis-type BWTS can be applied; however, salinity levels and regional regulations must be considered. A comparative analysis of suitable models will be provided for selection. | 3000
10918 | 9002 | LNG-DF-CNTR | 12000TEU | Kindly confirm the arrangement of the gas detection system in the engine room and LNG tank area. | Gas detection sensors are arranged per IGF Code and Class rules. We will share the layout drawings for your review and comments.
18597 | 9002 | LNG-DF-CNTR | 12000TEU | Please clarify the procedure for purging and inerting the LNG piping during gas trial preparation. | Purging and inerting procedures will follow maker guidelines and will be included in the Gas Trial Procedure document to be submitted for review and approval prior to commissioning. |  | 1600
10360 | 9002 | LNG-DF-CNTR | 12000TEU | We would like to request access ladders and maintenance platforms around the LNG fuel tank for easier inspection access. | We agree to install access ladders and maintenance platforms as per your request. A revised tank arrangement drawing will be shared shortly for your approval. | 2000